## Requirements
Project Requirements
PR | Requirement | Notes | Page | Status
PR_1 | Develop backend GET Api to provide all the available contents | /api/content | 2 | Done
PR_2 | Backend GET Api to provide filtered content | /api/movies /api/series /api/documentaries | 2 | Done
PR_3 | Backend POST Api to upload content to database | /api/create | 2 | Done
PR_4 | Backend DELETE Api to delete content from the database | /api/delete + {contentID}
PR_5 | Backend PUT Api to edit content | /api/update | 2 | Done
PR_6 | Backend API for login | /login - Note: in "security" branch | 2 | Done
PR_7 | Integrate Home page with backend API |  | 2 | Done
PR_8 | Integrate Content page with backend API |  | 2 | Done
PR_9 | Integrate Admin Page with backend API |  | 2 | Done
PR_10 | Integrate login with backend API | in security branch | 2 | In Progress

## Technical Requirements
Technical Requirements
TR | Requirement | Notes | Status
TR_1 | Create database in AWS RDS |  | Done
TR_2 | Create storage in AWS S3 |  | Done
TR_3 | Integrate AWS database with project |  | Done
TR_4 | Integrate AWS S3 bucket with project |  | Done
TR_5 | Include docker compose to rung the project from single point |  | Done